## Test Cases
TC ID | Module | Test Type | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result / Evidence from PDF | Execution Status | Pass/Fail | Evidence Reference | Notes / Follow-up
REG-001 | Registration Form | Positive | Submit registration with valid details and valid CAPTCHA | Registration page is open | Enter valid values in all required fields; complete CAPTCHA; click Send | Valid name, email, password and matching confirmation; valid CAPTCHA | Registration is accepted and success confirmation is shown | Screenshot shows registration form; no successful confirmation is visible in supplied screenshots. | Not Executed | Not Run | PDF page 1, upper screenshot | Requires live execution; do not infer success from filled fields.
REG-002 | Registration Form | Negative | Submit with all fields empty | Registration page is open | Leave all fields blank; click Send | Blank values | Required-field validation is shown and submission is blocked | No empty-submit attempt is evidenced in screenshots. | Not Executed | Not Run | PDF page 1, upper screenshot | Verify each required field and validation message.
REG-003 | Registration Form | Negative | Enter malformed email address | Registration page is open | Enter malformed email; fill other required fields; submit | name@invalid | Email validation appears and submission is blocked | No malformed-email attempt is evidenced. | Not Executed | Not Run | PDF page 1 | Test multiple malformed formats.
REG-004 | Registration Form | Negative | Enter mismatched password and confirmation | Registration page is open | Enter different values in password and confirmation; submit | Password A / Password B | Mismatch is reported; form is not accepted | No mismatch attempt is evidenced. | Not Executed | Not Run | PDF page 1 | Verify message and whether values are retained.
REG-005 | Registration Form | Negative | Submit with CAPTCHA missing or incorrect | Registration page is open | Complete required fields; omit or enter invalid CAPTCHA; click Send | Incorrect/blank CAPTCHA | Submission is rejected with a clear CAPTCHA error | Lower screenshot shows a red banner stating the system was unable to verify the user. | Screenshot Reviewed | Fail | PDF page 1, lower screenshot | Failure is visible for the pictured attempt; exact CAPTCHA input/action cannot be established from screenshot.
REG-006 | Registration Form | Positive | Verify field labels and form controls are visible | Registration page is open | Inspect form labels and controls | N/A | Relevant fields and Send button are visible and usable | Screenshot shows a registration form with multiple fields, a CAPTCHA area, and Send button. | Screenshot Reviewed | Pass | PDF page 1, upper screenshot | Visual presence only; usability not confirmed.
STU-001 | Student Registration Form | Positive | Submit student form with valid data | Student registration page is open | Enter valid name, email, gender, mobile, date, subjects/hobbies, address and location; submit | Valid sample values as shown in screenshot | Confirmation dialog displays submitted values | Screenshot shows a confirmation dialog titled “Thanks for submitting the form” with submitted field/value rows. | Screenshot Reviewed | Pass | PDF page 6 | Confirms visible submission result for the pictured attempt only.
STU-002 | Student Registration Form | Positive | Verify required fields accept valid entries | Student registration page is open | Enter values in required fields and inspect validation indicators | Values shown in screenshot | Valid fields are accepted and no validation errors remain | Screenshot shows green validation outlines/check marks for several populated fields. | Screenshot Reviewed | Pass | PDF page 5, lower screenshot | Visual evidence only; exact values and validation rules should be rechecked live.
STU-003 | Student Registration Form | Negative | Submit with required fields empty | Student registration page is open | Leave required fields blank; click Submit | Blank required values | Required-field errors appear and confirmation dialog does not open | No empty-submit attempt is shown. | Not Executed | Not Run | PDF pages 5–6 | Run live to confirm required-field rules.
STU-004 | Student Registration Form | Negative | Enter malformed email | Student registration page is open | Enter malformed email and attempt submission | not-an-email | Email validation appears; invalid form is blocked | No malformed-email attempt is shown. | Not Executed | Not Run | PDF page 5 | Check both inline validation and submission behavior.
STU-005 | Student Registration Form | Negative | Enter invalid mobile number | Student registration page is open | Enter alphabetic/too-short mobile number and submit | abc / 123 | Mobile validation appears and invalid submission is blocked | No invalid-mobile attempt is shown. | Not Executed | Not Run | PDF page 5 | Determine expected length/format from live application.
STU-006 | Student Registration Form | Positive | Close submission confirmation dialog | Submission confirmation dialog is open | Click Close | N/A | Dialog closes and form page is visible | Screenshot shows the confirmation dialog and a Close button, but not the result after clicking it. | Not Executed | Not Run | PDF page 6 | Requires live interaction.
CART-001 | Shopping Cart | Positive | Verify product and cart total for one item | Shopping cart page is open | Inspect product row, quantity and total | Quantity 1; displayed product price £55.00 | Cart shows item, quantity 1 and correct total | Screenshot shows one Grey Jacket, quantity 1, price £55.00 and total £55.00. | Screenshot Reviewed | Pass | PDF page 3, upper screenshot | Arithmetic/display verified from screenshot only.
CART-002 | Shopping Cart | Negative | Set product quantity to zero | Shopping cart page is open | Change quantity to 0; click Update | Quantity 0 | System prevents invalid quantity or removes item and recalculates total consistently | Screenshot shows a quantity value of 0 in the lower cart screenshot while the displayed total remains £55.00. | Screenshot Reviewed | Fail | PDF page 3, lower screenshot | Visible inconsistency: quantity 0 with total still £55.00. Reproduce live and inspect update behavior.
CART-003 | Shopping Cart | Negative | Set product quantity to a negative number | Shopping cart page is open | Enter -1 in quantity; click Update | Quantity -1 | Negative quantity is rejected or normalized; total must not remain misleading | Screenshot appears to show quantity -1 while total remains £55.00. | Screenshot Reviewed | Fail | PDF page 3, lower screenshot | Potential validation/calculation defect; confirm live.
CART-004 | Shopping Cart | Positive | Proceed to checkout from a valid cart | Cart contains a valid item and quantity | Click Check Out | Quantity 1 | Checkout page opens with cart summary and contact/delivery fields | Screenshot shows checkout page with contact, delivery and order summary sections. | Screenshot Reviewed | Pass | PDF page 4, upper screenshot | Navigation is evidenced by screenshot; successful click sequence is not independently verified.
CART-005 | Shopping Cart | Negative | Attempt checkout with required contact/delivery fields empty | Checkout page is open | Leave required fields blank and submit/continue | Blank email/address/name | Checkout blocks progression and indicates required fields | Screenshot shows checkout fields, but no empty-submit result. | Not Executed | Not Run | PDF page 4, upper screenshot | No order-submission control/result is visible in the provided image.
CART-006 | Shopping Cart | Negative | Apply an invalid discount code | Checkout page is open | Enter invalid discount code and click Apply | INVALIDCODE | Code is rejected with a clear message and totals remain correct | Screenshot shows a Discount code field and Apply button; no invalid-code result is shown. | Not Executed | Not Run | PDF page 4, upper screenshot | Requires live execution.
FORM-001 | ToolsQA Text Box Form | Positive | Submit valid text-box details | Text Box page is open | Enter full name, email, current address and permanent address; click Submit | Values visible in screenshot | Submitted values are displayed below the form | Screenshot shows submitted values displayed below the form after entry. | Screenshot Reviewed | Pass | PDF page 2, lower screenshot | Visible result supports successful submission for the pictured attempt.
FORM-002 | ToolsQA Text Box Form | Negative | Enter malformed email in text box form | Text Box page is open | Enter malformed email; fill other fields; submit | bad-email | Email validation appears or invalid email is handled according to form rules | Screenshot shows an email-like value but does not demonstrate malformed-email validation. | Not Executed | Not Run | PDF page 2 | Confirm whether this page validates email format.
FORM-003 | ToolsQA Text Box Form | Positive | Verify current and permanent address fields retain entered text | Text Box page is open | Enter different values in both address fields; submit | Current: Karachi Pakistan; Permanent: Karachi Pakistan | Both address values appear in output and are not mixed up | Screenshot output includes Current Address and Permanent Address values. | Screenshot Reviewed | Pass | PDF page 2, lower screenshot | The pictured values appear in the output.

## Execution Summary
Metric | Count / Result
Total test cases | 21
Screenshot Reviewed | 10
Not Executed | 11
Pass (screenshot evidence) | 7
Fail (screenshot evidence) | 3
Not Run | 11
Execution limitation | Only screenshots were supplied. No live application access or interactive execution was performed.
Evidence convention | Pass/Fail means the visible screenshot supports that check or defect observation; it is not a full live retest.

## Evidence Log
Evidence ID | PDF Page | Observed Evidence | Related Test Case(s) | Interpretation / Limitation
E-01 | 1 upper | Registration form with fields and Send button visible | REG-001, REG-002, REG-003, REG-004, REG-006 | Only visual presence is shown; no successful submission outcome.
E-02 | 1 lower | Red banner says unable to verify the user | REG-005 | Supports failure of pictured attempt; cannot determine exact input/action from screenshot.
E-03 | 2 upper/lower | Text Box form populated; output values displayed below form | FORM-001, FORM-003 | Visible submission output.
E-04 | 3 upper | Cart shows Grey Jacket, quantity 1, £55.00 total | CART-001 | Displayed total matches one item at £55.00.
E-05 | 3 lower | Cart screenshot appears to show quantity 0 / -1 while total remains £55.00 | CART-002, CART-003 | Potential defect; reproduce in live application before filing confirmed bug.
E-06 | 4 upper | Checkout page with contact/delivery and discount code fields | CART-004, CART-005, CART-006 | Page is visible; no validation or order completion outcome shown.
E-07 | 5 lower | Student form fields show green validation indicators | STU-002 | Visual validation indicators only.
E-08 | 6 | “Thanks for submitting the form” confirmation dialog lists submitted values | STU-001, STU-006 | Submission confirmation visible; closing behavior not shown.